## Sheet1
Issue Resolution Log
Column Definitions (important)
Issue ID – Reference from Issue Log
Issue Summary – Short description
Root Cause – Why it happened
Resolution Action – What was done
Verification Method – How closure was validated
Owner – Who fixed it
Final Status – Closed / Deferred
Resolution Date – When resolved
Resolution Type – Fix / Workaround / Process Change
Issue ID | Issue Summary | Root Cause | Resolution Action | Owner | Resolution Type | Resolution Date | Verification Method | Final Status
I-01 | Incomplete historical data | Legacy data gaps | Adjusted migration scope; validated critical records | Data Lead | Scope Adjustment | W26 | Migration validation report | Closed
I-02 | Vendor configuration delay | Resource constraints | Escalated via SLA; revised delivery plan | PM | Contract Escalation | W20 | Updated milestone approval | Closed
I-03 | Integration errors | API mismatch | Deployed hotfix and regression testing | IT Lead | Technical Fix | W29 | Integration test results | Closed
I-04 | Agent workflow confusion | Training gaps | Added refresher training sessions | Change Lead | Process Change | W35 | Training feedback survey | Closed
I-05 | High UAT defect count | Insufficient test coverage | Extended UAT window and prioritized defects | QA Lead | Schedule Adjustment | W37 | UAT sign-off | Closed
I-06 | Dashboard performance lag | Inefficient queries | Optimized reporting queries | Analytics Lead | Technical Fix | W34 | Performance benchmark | Closed
I-07 | Compliance approval delay | Late review cycle | Conducted early compliance review | Compliance | Process Change | W22 | Approval confirmation | Closed
I-08 | Go-live staffing shortage | Scheduling oversight | Approved temporary staffing plan | Ops Lead | Operational Fix | W39 | Go-live readiness check | Closed
T-09 | Go-live deployment | Execution | IT Lead | W39 | W40 | Not Started | UAT sign-off | —
T-10 | Stabilization & hypercare | Execution | Ops Lead | W41 | W44 | Not Started | Go-live | —