## Sheet1
Task Tracker
Column Definitions (important)
Task Name
Task ID
Status (Not Started / In Progress / Blocked / Completed)
Dependencies
Start Week
End Week
Allocation Level – Low / Medium / High
Notes / Blockers
Task ID | Task Name | Phase | Owner | Start Week | End Week | Status | Dependencies | Notes / Blockers
T-01 | Approve project charter | Initiation | Sponsor | W3 | W4 | Completed | Business case | —
T-02 | Finalize requirements | Planning | PM | W6 | W10 | Completed | Stakeholder inputs | —
T-03 | Select platform vendor | Planning | PM | W7 | W10 | Completed | Evaluation | —
T-04 | Configure core workflows | Execution | Vendor | W13 | W24 | In Progress | Requirements | On track
T-05 | Build system integrations | Execution | IT Lead | W17 | W30 | In Progress | Platform config | Minor defects
T-06 | Perform data migration | Execution | Data Lead | W25 | W32 | In Progress | Integration readiness | Legacy data gaps
T-07 | Conduct UAT | Execution | QA Lead | W31 | W36 | Not Started | Migration | —
T-08 | Deliver agent training | Execution | Change Lead | W33 | W36 | Not Started | UAT readiness | —
T-09 | Go-live deployment | Execution | IT Lead | W39 | W40 | Not Started | UAT sign-off | —
T-10 | Stabilization & hypercare | Execution | Ops Lead | W41 | W44 | Not Started | Go-live | —