## Sheet1
Dependency_Log
Customer Support System Transformation
Organization: Walmart
Framework: Traditional / Waterfall
Column Definitions
Dependency ID : Unique identifier
Dependent Activity : Work that depends on something else
Predecessor Activity : Required prior activity
Dependency Type : FS / SS / FF / External
Impact if Delayed : Schedule / Cost / Quality / Risk
Owner :Who manages the dependency
Status : Open / In Progress / Resolved
Legend
FS = Finish-to-Start
SS = Start-to-Start
FF = Finish-to-Finish
Dep ID+A19:G29 | Dependent Activity | Predecessor Activity | Dependency Type | Impact if Delayed | Owner | Status
D-01 | Platform configuration | Platform selection approval | FS | Schedule | PM | Open
D-02 | System integration | Platform configuration | FS | Schedule | IT Lead | Open
D-03 | Data migration | Integration readiness | FS | Schedule / Risk | IT Lead | Open
D-04 | Testing & validation | Data migration completion | FS | Quality | QA Lead | Open
D-05 | Training rollout | System stability confirmation | FS | Adoption | PM | Open
D-06 | Go-live decision | Successful UAT sign-off | FS | Schedule / Risk | Sponsor | Open
D-07 | Reporting dashboards | Data model finalization | FS | Quality | Analytics | Open
D-08 | Compliance approval | Security assessment | FS | Risk | Compliance | Open
D-09 | Vendor deliverables | Contract & SOW approval | External | Schedule | PM | Open
D-10 | Post-go-live support | Go-live completion | FS | Quality | Support Ops | Open