## Sheet1
Requirements_Traceability_Matrix (RTM)
Customer Support System Transformation
Organization: Walmart
Framework: Traditional / Waterfall
Column Definitions (important)
BR ID : Business Requirement
FR ID : Functional Requirement
DM : Data Migration Requirement
TR : Training Requirement
NFR ID : Non-Functional Requirement
Design Reference : Where it’s designed/configured
Test Case ID : How it’s validated
Status : Lifecycle tracking
BR ID | FR / NFR ID | Requirement Description | Design Reference | Test Case ID | Owner | Status
BR-01 | FR-01 | Unique case creation for customer issues | Case Mgmt Design | TC-01 | IT Lead | Approved
BR-01 | FR-02 | Case categorization & prioritization | Workflow Design | TC-02 | IT Lead | Approved
BR-01 | FR-03 | End-to-end case tracking | Case Lifecycle Design | TC-03 | IT Lead | Approved
BR-02 | FR-04 | Automated return workflows | Workflow Automation | TC-04 | Vendor | Approved
BR-02 | FR-05 | Automated refund approvals | Refund Flow Design | TC-05 | Vendor | Approved
BR-02 | FR-06 | Configurable escalation rules | SLA Configuration | TC-06 | IT Lead | Approved
BR-03 | FR-07 | Multi-channel integration | Channel Integration | TC-07 | Vendor | Approved
BR-03 | FR-08 | Unified customer interaction history | Data Model Design | TC-08 | Vendor | Approved
BR-04 | FR-09 | Real-time dashboards | Reporting Design | TC-09 | Analytics | Approved
BR-04 | FR-10 | SLA & resolution reports | Reporting Design | TC-10 | Analytics | Approved
BR-05 | NFR-01 | Support high concurrent users | Architecture Design | TC-11 | IT Lead | Approved
BR-05 | NFR-02 | Near real-time case updates | System Performance | TC-12 | IT Lead | Approved
BR-05 | NFR-03 | Data security compliance | Security Design | TC-13 | Compliance | Approved
BR-05 | NFR-04 | Role-based access control | Access Control Design | TC-14 | IT Lead | Approved
BR-05 | NFR-05 | High system availability | Infrastructure Design | TC-15 | IT Lead | Approved
BR-05 | NFR-06 | Backup & recovery support | DR Design | TC-16 | IT Lead | Approved
BR-01 | DM-01 | Historical data migration | Migration Plan | TC-17 | IT Lead | Approved
BR-01 | DM-02 | Active case validation | Migration Validation | TC-18 | IT Lead | Approved
BR-02 | TR-01 | Role-based training materials | Training Plan | TC-19 | PM | Approved
BR-02 | TR-02 | Agent training before go-live | Training Schedule | TC-20 | PM | Approved