## Sheet1
MILESTONE LIST
Milestone ID | Milestone Name | Description | Planned Week | Approval Authority | Dependencies | Status
M1 | Project Charter Approved | Formal authorization to start project | W4 | Executive Sponsor | Business Case | Approved
M2 | Planning Baseline Approved | Scope, schedule, and cost baselined | W12 | Executive Sponsor | Planning completion | Planned
M3 | Platform Vendor Selected | Platform & vendor contract finalized | W10 | Executive Sponsor | Evaluation & SOW | Planned
M4 | Solution Configuration Complete | Core platform configuration finalized | W28 | IT Lead | Build & config | Planned
M5 | System Integration Complete | All system integrations completed | W30 | IT Lead | Configuration | Planned
M6 | Data Migration Complete | Historical & active data migrated | W32 | IT Lead | Integration readiness | Planned
M7 | User Acceptance Testing Sign-Off | Business validates system readiness | W36 | Business Owner | Testing | Planned
M8 | Go-Live Approval | Authorization to deploy to production | W40 | Executive Sponsor | UAT sign-off | Planned
M9 | Post Go-Live Stabilization Complete | System stable & adoption confirmed | W44 | Ops Director | Go-live | Planned
M10 | Project Closure Approved | Formal project closure & handover | W52 | Executive Sponsor | Benefits review | Planned