## Sheet1
Project_Schedule.xlsx
Customer Support System Transformation
Organization: Walmart
Framework: Traditional / Waterfall
Project Duration: ~10 months
Column Guide
Task ID – Unique identifier
Task Name – Deliverable-focused
Phase – Waterfall phase
Start / End – Planned dates
Duration (Weeks) – Planning realism
Predecessor – From Dependency Log
Owner – Accountability
MASTER PROJECT SCHEDULE
Task ID | Task Name | Phase | Start | End | Duration (Weeks) | Predecessor | Owner
T1 | Project Initiation & Approval | Initiation | W1 | W4 | 4 | — | PM
T2 | Detailed Planning | Planning | W5 | W12 | 8 | T1 | PM
T3 | Platform Selection & Contracting | Planning | W6 | W10 | 5 | T1 | PM
T4 | Solution Design & Configuration | Execution | W13 | W28 | 16 | T3 | IT / Vendor
T5 | System Integration | Execution | W17 | W30 | 14 | T4 | IT
T6 | Data Migration | Execution | W25 | W32 | 8 | T5 | IT
T7 | Testing & Validation (UAT) | Execution | W31 | W36 | 6 | T6 | QA
T8 | Training & Change Enablement | Execution | W33 | W38 | 6 | T7 | PM
T9 | Go-Live & Rollout | Execution | W39 | W40 | 2 | T8 | PM
T10 | Post Go-Live Support | Execution | W41 | W44 | 4 | T9 | Ops
T11 | Performance Review & Optimization | Monitoring | W45 | W48 | 4 | T10 | PM
T12 | Project Closure | Closing | W49 | W52 | 4 | T11 | PM
Milestones
Milestone ID | Milestone Name | Planned Week | Approval Authority
M1 | Project Charter Approved | W4 | Sponsor
M2 | Planning Baseline Approved | W12 | Sponsor
M3 | Platform Contract Signed | W10 | Sponsor
M4 | Configuration Complete | W28 | IT Lead
M5 | Data Migration Complete | W32 | IT Lead
M6 | UAT Sign-Off | W36 | Business Owner
M7 | Go-Live Approval | W40 | Sponsor
M8 | Project Closure | W52 | Sponsor
Schedule_Baseline
Baseline Type | Approved Week | Notes
Schedule Baseline | W12 | Post-planning approval
Cost Baseline | W12 | Linked to budget
Scope Baseline | W12 | Via Scope Statement