## Sheet1
Cost Estimates
Cost ID | Cost Category | Description | Estimation Basis | Estimated Cost (USD) | Assumptions
C1 | Platform Licensing | Annual license for support platform | Industry benchmark | 1200000 | Enterprise user volume
C2 | Implementation Services | Vendor implementation & setup | Analogous project | 850000 | Fixed-scope contract
C3 | System Integration | Integration with OMS & payments | Effort-based | 600000 | Multiple systems
C4 | Data Migration | Historical & active data migration | Past migration avg | 400000 | Clean data availability
C5 | Testing & QA | UAT & validation activities | Resource estimate | 250000 | Internal + vendor
C6 | Training | Agent & manager training | Per-user estimate | 300000 | Large support teams
C7 | Change Management | Adoption & comms activities | % of project cost | 200000 | Enterprise change effort
C8 | Project Management | PM & governance overhead | % of total | 350000 | Full lifecycle
C9 | Contingency | Risk buffer | 10% of subtotal | 415000 | Migration risks