## Sheet1
ISSUE LOG
Issue ID | Issue Description | Category | Impact Area | Priority | Owner | Status | Resolution Summary | Closure Date
I-01 | Incomplete historical data from legacy system | Technical | Schedule | High | IT Lead | Resolved | Adjusted migration scope, validated critical data only | W26
I-02 | Delays in vendor configuration delivery | Vendor | Schedule | Medium | PM | Resolved | Escalated via SLA, re-baselined milestone | W20
I-03 | Integration errors with payment system | Technical | Quality | High | IT Lead | Resolved | Hotfix deployed, regression tested | W29
I-04 | Support agents unclear on new workflow steps | Change | Quality | Medium | Ops Lead | Resolved | Additional training sessions conducted | W35
I-05 | UAT defects higher than expected | Quality | Schedule | Medium | QA Lead | Resolved | Extended UAT window by 1 week | W37
I-06 | Reporting dashboard performance lag | Technical | Quality | Low | Analytics | Resolved | Optimized queries, improved response time | W34
I-07 | Dependency delay from compliance approval | Governance | Schedule | Medium | Compliance | Resolved | Early review conducted, approval expedited | W22
I-08 | Go-live weekend staffing shortage | Operational | Risk | High | Ops Lead | Resolved | Temporary staffing plan approved | W39
I-09 | Change request overlap during stabilization | Change | Scope | Low | PM | Resolved | Deferred non-critical changes post go-live | W42