## Sheet1
RISK REGISTER
Risk ID | Risk Description | Category | Root Cause | Probability | Impact | Risk Score | Response Strategy | Mitigation Actions | Owner | Status
R-01 | Data loss during migration | Technical | Legacy data complexity | Medium | High | High 2 | Mitigate | Phased migration, backups, validation | IT Lead | Open
R-02 | Integration failures | Technical | Multiple upstream systems | Medium | High | High | Mitigate | Early integration testing | IT Lead | Open
R-03 | Platform performance issues | Technical | High transaction volume | Low | High | Medium | Mitigate | Load & stress testing | Vendor
R-04 | Vendor delivery delays | Vendor | Resource constraints | Medium | Medium | Medium | Transfer | Contract SLAs & penalties | PM
R-05 | Resistance from support agents | Change | New workflows | High | Medium | High | Mitigate | Training, comms, champions | Ops
R-06 | Inadequate training effectiveness | Change | Compressed timelines | Medium | Medium | Medium | Mitigate | Role-based training | PM
R-07 | Scope creep | Governance | Stakeholder pressure | Medium | Medium | Medium | Avoid | Formal change control | PM
R-08 | Budget overrun | Financial | Underestimated effort | Low | Medium | Low | Accept | Contingency reserve | Finance
R-09 | Go-live disruption | Operational | Cutover issues | Low | High | Medium | Mitigate | Parallel run & rollback | IT
R-10 | Compliance or data privacy issues | Compliance | Regulatory gaps | Low | High | Medium | Avoid | Security reviews & audits | Compliance
R-11 | Inaccurate benefit realization | Business | Optimistic assumptions | Medium | Medium | Medium | Accept | Post-implementation review | Sponsor
R-12 | Dependency delays | Schedule | External approvals | Medium | Medium | Medium | Mitigate | Dependency tracking | PM