## Sheet1
Change Log
Column Definitions (important)
Change ID – Unique identifier
Change Request Title – Short, clear summary
Change Type – Scope / Schedule / Cost / Quality / Process
Description – What is changing
Requested By – Stakeholder
Impact Summary – Schedule / Cost / Risk impact
Decision – Approved / Rejected / Deferred
Implementation Status – Pending / Implemented
Decision Date
Change ID | Change Request Title | Change Type | Description | Requested By | Impact Summary | Decision | Approval Authority | Implementation Status | Decision Date
CR-01 | Extend UAT duration | Schedule | Extend UAT by 1 week due to defect volume | Business Owner | 1 week schedule | Approved | Executive Sponsor | Implemented | W34
CR-02 | Defer non-critical reporting features | Scope | Move low-priority reports to post go-live | PM | Reduced risk, no cost impact | Approved | Executive Sponsor | Implemented | W32
CR-03 | Additional agent training session | Process | Add refresher training before go-live | Ops Lead | Minor cost, adoption benefit | Approved | PM | Implemented | W36
CR-04 | Adjust data migration scope | Scope | Exclude low-value historical data | IT Lead | Reduced migration risk | Approved | Executive Sponsor | Implemented | W25
CR-05 | Request parallel run extension | Schedule | Extend parallel run by 1 week | Ops Lead | 1 week support effort | Deferred | Executive Sponsor | Not Implemented | W40
CR-06 | Add dashboard performance optimization | Quality | Improve response time of dashboards | Analytics | No schedule impact | Approved | PM | Implemented | W33