## Sheet1
Resource Plan
Column Definitions (important)
Role – Position, not individual names
Department / Type – Business / IT / Vendor
Project Phase – Where effort is concentrated
Responsibility – What they contribute
Allocation Level – Low / Medium / High
Engagement Type – Full-time / Part-time / On-demand
Role | Department / Type | Project Phase | Responsibility | Allocation Level | Engagement Type
Executive Sponsor (VP CX) | Business | Initiation, Governance | Strategic direction, approvals | Low | On-demand
Project Manager | PMO | All phases | End-to-end delivery & control | High | Full-time
Support Operations Director | Business | Planning, Execution | Business ownership, adoption | Medium | Part-time
Customer Support Managers | Operations | Execution, Rollout | Team readiness & feedback | Medium | Part-time
Support Agents (Pilot Group) | Operations | Testing, Rollout | UAT & early adoption | Low | Part-time
IT Systems Lead | IT | Planning, Execution | Technical oversight & integration | High | Full-time
Integration Engineers | IT | Execution | System integration work | High | Full-time
Data Migration Specialist | IT | Execution | Data migration & validation | Medium | Part-time
QA / Testing Lead | IT | Testing | Test coordination & defect mgmt | Medium | Part-time
Analytics / Reporting Lead | Analytics | Execution | Dashboards & reporting | Low | Part-time
Change & Training Lead | Business | Rollout | Training & adoption support | Medium | Part-time
Platform Vendor Team | Vendor | Execution | Configuration & support | High | Contracted
Compliance & Security Lead | Risk / Compliance | Planning, Review | Security & regulatory checks | Low | On-demand